## Classified LAS
Burnett County LiDAR East Area (1067 Tiles)
2016-01-12
| Acceptance Criteria | PCM Comments | Ayres Reponse | PCM Back Check | Ayres Reponse | PCM Back Check
LiDAR Accuracy Assessment
Vertical Accuracy Assessment | FVA <= 18.5 cm(0.61 feet) RMSEz 36.3cm (1.2 feet), 95th % confidence Level SVA <= 36.3 cm (1.2 ft), 95th Percentile CVA <= 36.3 cm (1.2 ft), 95th Percentile NSSDA Accuracy Test | Pass Class RMSE 95%'tile All 0.30 0.60 B/E 0.20 0.32 Brush 0.24 0.46 LowVeg 0.58 1.19 Forested 0.25 0.49 Urban 0.25 0.30 | No Response No Response No Response
Horizontal Accuracy Assessment | RMSEr <= 2.2 feet Accuracy <= 3.8 feet @ 95th Confidence Level | Pass
Ground Control in ASCII format |  | Fail No data was furnished. |  | Fail No data was furnished. | Will deliver, typically done at final delievery. | Accepted
LiDAR Quality Assessment
Pre-Flight Plan | Flight lines flown as planned with 50% sidelap, correct altitude of 1700 meters, 500 foot buffer around county boundary. Base Stations within 20 km.
Flight Lines | Flight lines flown as planned with 50% sidelap, correct altitude of 1700 meters, 500 foot buffer around county boundary.
Raw Point Cloud | LAS Swaths with SBET's and Trajectory Files
Base Stations | Within 20 km of any area within county
QA/QC Plan | As per proposal
SBET's | Forward and Reverse comparisons within 4-8 cm
Readability | Files readable with 2 different software packages | Pass
Tile Size | 5000 ft x 5000 ft | Pass
Tile Schematic | ESRI Shapefile format | Pass
File Naming | As per provided shape file | Pass
Georeferencing | Opens in correct location according to county furnished tile grid layout | Pass
Project Coverage | Burnett County plus a 100 foot buffer and 1000 feet on west side | Pass
Scan Angle | "+/- 20 degrees from nadir"
Sidelap | Minimum 30% | Fail There is no overlap between N-S flights in the SW corner of the project and the remaining flights. |  | Fail There is no overlap between N-S flights in the SW corner of the project and the adjacent flights. | We do not delete data and there is no gap in coverage. Additional overlap would not change results but would only increase the size of the data. | See Figure 1 below. Agreed that there is no gap in coverage, however, it is highly unlikely that the sensor can be set to stop coverage along a line as shown. Therefore the data must exist and since it is not shown it must have been removed/deleted from the delivery materials. In Figure 1A there is missing coverage on two of the flights lines in the overlap area. Having the data cut along the tile boundaries indictes a processing error.
Data Voids | None | None
Low Confidence Polygons | Using a 1 meter grid the points are < NPS for areas 5 acre and over
Point Density | 1.0 ppsm | Pass Average over non-water first return > 2 ppsm
Horizontal Datum | NAD_1983_HARN_WISCRS_Burnett_County_Feet¦projection: Lambert Conic Conformal (2SP) | Pass
Vertical Datum | NAVD88 - Geoid12A (Feet) | Pass
Units | US Feet | Pass
Projection | Burnett County - Wisconsin Coordinate Reference System | Pass
LAS Version | 1.2 | Pass
LAS Header Information | VLR's contain Georeferencing information | Pass
Point Cloud | Existence of: GPS Time Stamps Easting Northing Elevation Intensity Return Number Return Classification Point Source ID | Pass
Duplicates | None Allowed | Fail The following tiles have duplicate points. Tile # Duplicates 2812.las 4861622 3519.las 4202842 3520.las 3275762 3419.las 2574664 3418.las 967753 3518.las 733240 3741.las 35 3543.las 22 3840.las 4 2712.las 1 |  | Pass
Calibration Flight lines | ??? | Fail None Apparent |  | Fail None Apparent | Calibration Flight Lines have been removed from the delivered point cloud. | Accepted
Classes | 1 Unclassified 2 Ground 5 High Vegetation (>10') 6 Buildings 7 Low Points 9 Water 10 Hydro buffer points 11 Withheld points 17 Bridges 18 Anomalies | Pass with Errors Classifications are as per contract except Class 17 (bridges), which is acceptable, and Class 18 (????) were added. Class 18 appears to be low noise of a sensor error type. Class 18 is normally used for High Noise but in this case it is used for Low Noise and should be placed in Class 7. Tiles 1533, 3126, 3742, 3942, 3943, 3940, 2937, 2822, 1633, 3840, 1738, 3844, 3845, 3127, 1142, 1543, 2338, 3228, 1531, 1736, 1740, 3541 and 3941 contain Class 18 points. Also, it appears that the Class 18 points are due to a sensor error rather than simply random noise. There are some extraneous bridge points (Class 17) that are obviously not bridges. Please see the QR comments shape file. There are quite a few calls regarding bulding classifications (Class 6). Because these were classified using automated routines and no accuracy was specified these are provided for informational purposes only. |  | High Veg points in water were not corrected as identified in the QR_Comments shape file. There are some extraneous bridge points (Class 17) that are obviously not bridges. Please see the QR comments shape file. There are quite a few calls regarding building classifications (Class 6). Because these were classified using automated routines and no accuracy was specified these are provided for informational purposes only. Calls made regarding gaps in coverage and overlap between flight lines were not addressed. Areas that are classified as water but is probably ground have not been addressed. | Removing high vegetation points from the water will result in trees that overhang the banks being essentially "clipped". Manual cleanup of the high vegetation class is not part of the contract specs as these were automated routines in which best parameters were used and not intended to be perfect classification of the vegetation. The majority of the extraneous bridge points have been addressed. There were a couple situations were point were left as bridges as that these verified based on the 2015 ortho. Building classification per contract specs is an automated routine and manual edits were performed on buildings to a at the descretion of the editors to aid in classification improvement. No additional manual review of the building classification has been performed. | See Figure 2 regarding high class 1 points in the water. These points show up in the DSM. These are not overhanging trees. DEM is fine. See Figure 3 regarding Class 1 points showing up in water and affecting the DSM. See Figure 4, 5, 6, 7, 8, 9 and 10 regarding Vegetation and Class 1 points showing up in water. See Figure 11 for an example of mis-identified bridge points. Explanation regarding building classifications are acceptable. Areas that are classified as water but is probably ground have not been addressed. See Figure 12 and 12A as a representative sample.
Bare Earth Only | las format | Pass
Proper Classification | Within any 1 km x 1 km area, no more that 2 percent of non-withheld points will possess a demonstrably erroneous classification value | Pass
Data Consistency (No seam lines) Relative Accuracy | Within Individual Swaths <= 7 cm RMSEz Within Overlap between Swaths <= 10 cm RMSEz | Pass
Other |  | None
Contours | Correct Interval - 2' Indexes Cartographic Quality No Crossing Contours Labeling Bridges removed Contours are topologicallty correct Consistent feature classes | Pass
Hydro Enforcement - Inland Lakes/Ponds | 2 Acres or greater Flat and Level Water Bodies Buffer around Break Lines ESRI Feature Class PolylineZ or PolygonZ | Pass
Hydro Enforcement - Streams and Rivers | 20 foot and wider Flat and level bank-to-bank Smooth, continous and monotonic No stair steps Buffer around Break Lines ESRI Feature Class PolylineZ | Pass
DEM's | ESRI GRID format Grid Size of 3.125 feet 1600 x 1600 grids (5000' x 5000' tile size) Correct tile size and naming convention Break line enforced | Pass with Errors Along the edges of the project boundary, some corners of some DEM's need to be trimmed to eliminate interpolation along inside edges resulting in erroroneous elevations. |  | Pass Only perimeter tiles were submitted and those have been corrected at the sharp corners ths eliminated incorrect interpolations. Fail Since no corrections were made to the las files concerning high veg in water areas, the DEM's will also have the erroroneous points. | Manual classification of high vegetation points over water points is outside of contract specs. Building and high vegetation classification are automated routines that in some instances are not exact over bodies of water. Both Building and veg classes on not utilized on the DEM, only ground and breaklines are used. | Accepted
DSM's | ESRI GRID format Grid size of 3.125 feet 1600 x 1600 grids (5000' x 5000' tile size) Created using only first returns Correct tile size and naming convention | Fail ?? It appears that Class 1 (Unclassified) was used in the creation of the DSM's. Class 1 includes items such as vehicles and erroroneous high vegetation in water, which should not be included in a DSM. |  | Fail It appears that the Class 1 returns were removed from the DSM's but there are still areas in the water that include high vegetation. | Manual cleanup of high vegetation points over water is outside contract specs as these are automated routines that are not intended to be exact from a clasification standpoint on features above the water or the ground surface. | Agree with comments regarding trees overhanging the waters edge. However, vegetation in the middle of water bodies indicate a sensor error or errors in classifications. These are so obvious that other users of the data will probably question the quality of the data.
Intensity Images | ESRI GRID format Correct tile size and naming convention Correct format | Pass
MetaData | FGDC Compliant | Fail None submitted. |  | Fail None submitted. | Metadata will be provided at final delievery | Accepted
Ayres Internal QC Forms
Automated QR: For the items that are checked using automated routines, there should be a 100% compliance with the specifications. For example, all tiles are expected to have the correct projection.
Manual QR: A random sampling of the tiles in each delivery will be reviewed according to the criteria in the above table.
During the QR, each checklist item has three possible outcomes:
1. Pass with No Errors Noted – Review for the checklist item is complete. No further action required.
2. Pass with Errors Noted – Review for the checklist item is complete except for a few errors observed within the review area. A list of the errors and associated shapefile(s) will be provided. Ayres will be required to correct the identified errors and any other similar errors throughout the entire block. A back-check review will be conducted when the block is resubmitted.
3. Fail – All locations where errors are observed for the failed checklist item will be documented. However, PCM will only provide three (3) to five (5) examples, with an associated shapefile, of why the checklist item failed. Note that the checklist items will be reviewed in parallel for each tile. When a checklist item fails, PCM will stop the QA review for the failed checklist item but will continue with QA review of the other checklist items for the tile currently under review and all remaining tiles under review. PCM will not provide a list of tiles reviewed or the percentage of tiles reviewed. Ayres will be required to correct these types of errors throughout the entire block and resubmit to PCM. An PCM back-check review will be conducted when the block is resubmitted. If five (5) percent or more of the observed errors are not corrected on the resubmittal, the block will fail again for the checklist item. Another randomly selected 20 percent of the block’s tiles will be reviewed for the failed checklist item.
Figure 1: Lack of overlap/sidelap between adjacent flight lines
Figure 1A: The flight swath protrayed in green is clipped at the tile boundaries. The same for the flight swath protrayed in blue.
Figure 3A: DSM
Figure 2: Unclassified points show up in middle of water body. These data points also show up in the DSM. The DEM is fine.
Figure 3A: DSM
Figure 3: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 4A: DSM
Figure 4: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 5A: DSM
Figure 5: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 6A: DSM
Figure 6: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 7: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 8: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 9: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 10: Vegetation and Class 1 points show up in a waterbody. DSM contain Class 1 points, DEM is fine.
Figure 11: One example of mis-identified bridge points.
Figure 12: Ground Point in Water Body |  | Figure 12A: Digital Orthoof water Body

## Bare Earth
Burnett County LiDAR East Area (16 Tiles)
2015-08-27
| Acceptance Criteria | PCM Comments | Ayres Reponse | PCM Back Check | Ayres Reponse
LiDAR Accuracy Assessment
Vertical Accuracy Assessment | FVA <= 18.5 cm(0.61 feet) RMSEz 36.3cm (1.2 feet), 95th % confidence Level SVA <= 36.3 cm (1.2 ft), 95th Percentile CVA <= 36.3 cm (1.2 ft), 95th Percentile NSSDA Accuracy Test | Pass Class RMSE B/E 0.275
Horizontal Accuracy Assessment | RMSEr <= 2.2 feet Accuracy <= 3.8 feet @ 95th Confidence Level
Ground Control in ASCII format |  | Missing
LiDAR Quality Assessment
Pre-Flight Plan | Flight lines flown as planned with 50% sidelap, correct altitude of 1700 meters, 500 foot buffer around county boundary. Base Stations within 20 km.
Flight Lines | Flight lines flown as planned with 50% sidelap, correct altitude of 1700 meters, 500 foot buffer around county boundary.
Raw Point Cloud | LAS Swaths with SBET's and Trajectory Files
Base Stations | Within 20 km of any area within county
QA/QC Plan | As per proposal
SBET's | Forward and Reverse comparisons within 4-8 cm
Readability | Files readable with 2 different software packages | Pass
Tile Size | 5000 ft x 5000 ft | Pass
Tile Schematic | ESRI Shapefile format | Pass
File Naming | As per provided shape file | Pass
Georeferencing | Opens in correct location according to county furnished tile grid layout | Pass
Project Coverage | Burnett County plus a 100 foot buffer and 1000 feet on west side | Pass
Scan Angle | "+/- 20 degrees from nadir"
Sidelap | Minimum 30% | Pass
Data Voids | None | Pass
Low Confidence Polygons | Using a 1 meter grid the points are < NPS for areas 5 acre and over
Point Density | 1.0 ppsm | Pass
Horizontal Datum | NAD_1983_HARN_WISCRS_Burnett_County_Feet¦projection: Lambert Conic Conformal (2SP) | Fail LAS files do not contain any georeferencing information |  | Pass
Vertical Datum | NAVD88 - Geoid12A (Feet) | Fail LAS files do not contain any georeferencing information |  | Pass
Units | US Feet | Fail LAS files do not contain any georeferencing information |  | Pass
Projection | Burnett County - Wisconsin Coordinate Reference System | Fail LAS files do not contain any georeferencing information |  | Pass
LAS Version | 1.2 | Pass
LAS Header Information | VLR's contain Georeferencing information | Fail LAS files do not contain any georeferencing information |  | Pass
Point Cloud | Existence of: GPS Time Stamps Easting Northing Elevation Intensity Return Number Return Classification Point Source ID | Pass
Duplicates | None Allowed | Pass
Calibration Flight lines | ??? | None shown in Pilot Area.
Classes | 1 Unclassified 2 Ground 3 Low Vegetation ( < 4') 4 Medium Vegetation (4'-12') 5 High Vegetation (>10') 6 Buildings 7 Low Points 9 Water 10 Hydro buffer points 11 Withheld points 13 Bridges 14 Dams 21 High Points | Pass Only ground classes are present
Bare Earth Classification | 98% of Artifacts removed 98% of Outliers removed 98% of Buildings removed 95% of Vegetation removed | Pass
Proper Classification | Within any 1 km x 1 km area, no more that 2 percent of non-withheld points will possess a demonstrably erroneous classification value | Pass
Data Consistency (No seam lines) Relative Accuracy | Within Individual Swaths <= 7 cm RMSEz Within Overlap between Swaths <= 10 cm RMSEz Check DZ ortho's | Pass
Bare Earth Classification | Only Bare Earth LiDAR points | Fail Duplicate points in tiles 3840, 3741, 3543, 3520, 3519, 3518, 3419, 3418, and 2812 |  | Fail Duplicate points in tiles 3840, 3741, 3543, 3520, 3519, 3518, 3419, 3418, and 2812 | Corrected
Other | Point Counts should be the same as the Classified Point Cloud | Paas The are differences in the total point counts for Class 2 but these are less than 20 points and are considered insignificant.
Contours | Correct Interval - 2' Indexes Cartographic Quality No Crossing Contours Labeling Bridges removed Minimum 100 sq ft for closed contours Contours are topologicallty correct Consistent feature classes | Pass
Hydro Enforcement - Inland Lakes/Ponds | 2 Acres or greater Flat and Level Water Bodies Buffer around Break Lines ESRI Feature Class PolylineZ or PolygonZ | Pass
Hydro Enforcement - Streams and Rivers | 20 foot and wider Flat and level bank-to-bank Smooth, continous and monotonic No stair steps Buffer around Break Lines ESRI Feature Class PolylineZ | Pass
DEM's | ESRI GRID format Grid Size of 3.125 feet 1600 x 1600 grids (5000' x 5000' tile size) Correct tile size and naming convention Break line enforced | Pass
DSM's | ESRI GRID format Grid size of 3.125 feet 1600 x 1600 grids (5000' x 5000' tile size) Created using only first returns Correct tile size and naming convention | Pass
Intensity Images | ESRI GRID format Correct tile size and naming convention Correct format | Pass
MetaData | FGDC Compliant | None submitted. Metadata will be reviewed on the final submittal.
Ayres Internal QC Forms
Automated QR: For the items that are checked using automated routines, there should be a 100% compliance with the specifications. For example, all tiles are expected to have the correct projection.
Manual QR: A random sampling of the tiles in each delivery will be reviewed according to the criteria in the above table.
During the QR, each checklist item has three possible outcomes:
1. Pass with No Errors Noted – Review for the checklist item is complete. No further action required.
2. Pass with Errors Noted – Review for the checklist item is complete except for a few errors observed within the review area. A list of the errors and associated shapefile(s) will be provided. Ayres will be required to correct the identified errors and any other similar errors throughout the entire block. A back-check review will be conducted when the block is resubmitted.
3. Fail – All locations where errors are observed for the failed checklist item will be documented. However, Atkins will only provide three (3) to five (5) examples, with an associated shapefile, of why the checklist item failed. Note that the checklist items will be reviewed in parallel for each tile. When a checklist item fails, Atkins will stop the QA review for the failed checklist item but will continue with QA review of the other checklist items for the tile currently under review and all remaining tiles under review. Atkins will not provide a list of tiles reviewed or the percentage of tiles reviewed. Ayres will be required to correct these types of errors throughout the entire block and resubmit to Atkins. An Atkins back-check review will be conducted when the block is resubmitted. If five (5) percent or more of the observed errors are not corrected on the resubmittal, the block will fail again for the checklist item. Another randomly selected 20 percent of the block’s tiles will be reviewed for the failed checklist item.